## Adrian Angeles
To-do list
To be completed by: |  |  |  | Name: Adrian Angeles
Deadline: |  |  |  | Date: 10/17/25
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-10-13 | 2025-10-14 | 2025-10-14 | 1 Day | Set up Initial Meeting
100% | Preparation | 2025-10-14 | 2025-10-14 | 2025-10-14 | 1 Day | Created Gantt Chart
100% | Create Queries | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2 Days
100% | Create Markdown | 2025-10-15 | 2025-10-15 | 2025-10-16 | 1 Day
100% | Feedback Session | 2025-10-16 | 2025-10-16 | 2025-10-16 | 1 Day | 2nd Group Meeting
100% | Assist With Charts | 2025-10-16 | 2025-10-16 | 2025-10-16 |  | Assist in Todo lists and Update Gantt Chart
100% | Pair Recording Session | 2025-10-16 | 2025-10-16 | 2025-10-16 | 1 Day | Set up call on Discord

## Aditya Dwivedi
To-do list
To be completed by: |  |  |  | Name: Aditya Dwivedi
Deadline: |  |  |  | Date: 10/17
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Took Video Editing Role | 2025-10-13 | 2025-10-14 | 2025-10-14 | 1Day
75% | Set up Editing Environment | 2025-10-13 | 2025-10-13 | 2025-10-13 | 1 Day | Prepared Tools Needed to Edit Videos
50% | Query Creation | 2025-10-14 | 2025-10-14 | 2025-10-15 | 1Day
25% | Markdown Creaton | 2025-10-15 | 2025-10-15 | 2025-10-15 | 1DDay
0% | Set Up 2nd Meeting | 2025-10-16 | 2025-10-16 | 2025-10-16 | 1D | Set Up The 2nd Peer Review Meeting
0% | Pair Recording | 2025-10-16 | 2025-10-16 | 2025-10-16 | 1D | Created a Google Meeting for recording
0% | Combine Videos | 2025-10-16 | 2025-10-16 | 2025-10-16 | 1D | Join The Individual Videos together
0% | Hand-off | 2025-10-16 | 2025-10-17 | 2025-10-17 | 1Day | Handed In the Combined Video

## Ali Mustafa
To-do list
To be completed by: |  |  |  | Name: Ali Mustafa
Deadline: |  |  |  | Date: 10/17
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Delegated Tasks | 2025-10-13 | 2025-10-14 | 2025-10-14 | 1 Day | Assigned Tasks to each Member
75% | Check Up On Members | 2025-10-14 | 2025-10-14 | 2025-10-14 | 1 Day | Checked In on Progress
50% | Update Github Repo | 2025-10-14 | 2025-10-14 | 2025-10-14 | 1 Day | Created New Section on the Repository for the Assignment
25% | Query Creation | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2Day
0% | Markdown Creation | 2025-10-15 | 2025-10-15 | 2025-10-16 | 1Day
0% | Feedback Session | 2025-10-16 | 2025-10-16 | 2025-10-16 | 1Day | Gave Feedback to Others
0% | Gather Individual Files | 2025-10-16 | 2025-10-16 | 2025-10-17 | 1Day
0% | Submission | 2025-10-16 | 2025-10-17 | 2025-10-17 | 1Day | Updated the Repository and Submit every File Needed

## Mret Hein
To-do list
To be completed by: |  |  |  | Name: Mret Hein
Deadline: |  |  |  | Date: 10/17
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-12-10 | 2025-12-13 | 2025-12-13 | 1 Day | Offered Assitance to Group
100% | Preparation | 2025-12-11 | 2025-12-13 | 2025-12-13 | 1 Day | Helped Brainstorm Ideas and Areas that Needed Improvement
100% | Query Creation | 2025-12-14 | 2025-12-14 | 2025-12-14 | 1Day | Helped check the group's queries use set operators
100% | Markdown Creation | 2025-12-14 | 2025-12-14 | 2025-12-14 | 1Day
100% | Error Assistance | 2025-12-15 | 2025-12-15 | 2025-12-15 | 1Day | Peer Reviewed Other Member's Notebooks
100% | Format Review | 2025-12-15 | 2025-12-15 | 2025-12-15 | 1Day | Helped Make Every File and Chart more Cohesive
100% | FeedBack Session | 2025-12-16 | 2025-12-16 | 2025-12-16 | 1Day | Helped Offer Solutions to Problems
100% | Pair Recording | 2025-12-16 | 2025-12-16 | 2025-12-16 | 1Day | Decided on doing a double take