## Mret Hein
To-do list
To be completed by: |  |  |  | Name Mret Hein
Deadline: |  |  |  | Date 12/16/2025
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Review full project specification as a group | 2025-12-10 | 2025-12-10 | 2025-12-11 | 2 | Aditya was not free, so we recorded a video of our session so he can catch up
100% | Define team roles & responsibilities | 2025-12-11 | 2025-12-11 | 2025-12-11 | 1 | Member A–D assigned
100% | Create unified project plan / To-Do list | 2025-12-11 | 2025-12-11 | 2025-12-11 | 1 | Single shared file
100% | Normalize Uploadfile table | 2025-12-12 | 2025-12-12 | 2025-12-12 | 1
100% | Create UDT schema & types (01_UDT.sql) | 2025-12-13 | 2025-12-13 | 2025-12-13 | 1
100% | Create DbSecurity.UserAuthorization | 2025-12-13 | 2025-12-13 | 2025-12-13 | 1
100% | Design constraint strategy | 2025-12-13 | 2025-12-13 | 2025-12-14 | 2
100% | Implement constraint library (04_Constraint_Library.sql) | 2025-12-13 | 2025-12-13 | 2025-12-14 | 2
100% | Validate constraints via metadata view | 2025-12-14 | 2025-12-14 | 2025-12-14 | 1
100% | Slides creation | 2025-12-15 | 2025-12-15 | 2025-12-15 | 1
100% | Github setup & README.md creation | 2025-12-16 | 2025-12-16 | 2025-12-16 | 1
100% | Video Presentation | 2025-12-16 | 2025-12-16 | 2025-12-16 | 1
100% | Follow-up | 2025-12-15 | 2025-12-16 | 2025-12-16 | 2 | Check up on everyone's tasks and aid when one's having troubles

## Adrian
To-do list
To be completed by: |  |  |  | Name Mret Hein
Deadline: |  |  |  | Date 12/16/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Review full project specification as a group | 2025-12-10 | 2025-12-10 | 2025-12-11 | 1 | Aditya was not free, so we recorded a video of our session so he can catch up
100% | Analyze Uploadfile anomalies (input data) | 2025-12-10 | 2025-12-10 | 2025-12-10 | 1
100% | Design CDM, LDM, PDM | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2 | Difficulty trying to actually find how to draw such models on non-pay softwares
100% | Create normalized table structures: | 2025-12-12 | 2025-12-12 | 2025-12-12 | 1
100% | Define primary key / foreign key relationships Generate ERD diagrams in SQLDBM | 2025-12-10 | 2025-12-11 | 2025-12-12 | 3 | SQLDBM takes some time to navigate
100% | Provide ERD screenshots: | 2025-12-15 | 2025-12-15 | 2025-12-15 | 1
100% | Slides creation | 2025-12-15 | 2025-12-15 | 2025-12-15 | 1
100% | Video Presentation | 2025-12-16 | 2025-12-16 | 2025-12-16 | 1

## Aditya
To-do list
To be completed by: |  |  |  | Name Mret Hein
Deadline: |  |  |  | Date 12/16/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Review full project specification as a group | 2025-12-10 | 2025-12-11 | 2025-12-11 | 1 | Aditya was not free, so we recorded a video of our session so he can catch up
100% | Create ETL stored procedures: | 2025-12-13 | 2025-12-13 | 2025-12-14 | 2 | We referenced previous groups' work to help create stored procedures
100% | Create inline table-valued functions as ETL sources | 2025-12-14 | 2025-12-14 | 2025-12-14 | 1
100% | Create master load stored procedure
100% | Implement Process.WorkflowSteps logic, Process.usp_TrackWorkflow, Process.usp_ShowWorkflowSteps | 2025-12-13 | 2025-12-13 | 2025-12-14 | 2
100% | Execute stored procedures via JDBC Display results using Jtable | 2025-12-14 | 2025-12-14 | 2025-12-14 | 1
100% | Slides creation | 2025-12-15 | 2025-12-15 | 2025-12-15 | 1
100% | Video Presentation and video editing | 2025-12-16 | 2025-12-16 | 2025-12-16 | 1 | Stiched up and edited everyone's videos

## Ali
To-do list
To be completed by: |  |  |  | Name Mret Hein
Deadline: |  |  |  | Date 12/16/2025
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Review full project specification as a group | 2025-12-10 | 2025-12-10 | 2025-12-11 | 1 | Aditya was not free, so we recorded a video of our session so he can catch up
100% | Powerpoint Presentation set up | 2025-12-11 | 2025-12-11 | 2025-12-11 | 1
100% | Come up with propositions for queries | 2025-12-12 | 2025-12-12 | 2025-12-12 | 1
100% | Design 10 additional analytical queries | 2025-12-14 | 2025-12-14 | 2025-12-14 | 1
100% | Validate database design through query results Provide query result screenshots | 2025-12-15 | 2025-12-15 | 2025-12-15 | 1
100% | Assist with query-focused presentation slides, Explain how queries support design decisions | 2025-12-16 | 2025-12-16 | 2025-12-16 | 1
100% | Video Presentation | 2025-12-16 | 2025-12-16 | 2025-12-16 | 1
100% | Follow-up