## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Initial Meeting | 1 | 2 | 1 | 2 | 100%
Proj. Overview | 1 | 3 | 1 | 4 | 100%
Task Delegation | 2 | 4 | 2 | 5 | 100%
Material Review | 5 | 3 | 5 | 3 | 100%
2nd Group Meeting | 6 | 2 | 6 | 2 | 100%
Powerpoint Creation | 7 | 1 | 7 | 1 | 100%
Data Analysis | 7 | 1 | 7 | 2 | 100%
Normalization | 8 | 2 | 8 | 3 | 100%
Diagram Generation | 10 | 1 | 10 | 1 | 100%
UDT/Table Script Making | 8 | 2 | 8 | 3 | 100%
Constraint Creation | 8 | 2 | 8 | 3 | 100%
Stored Procedure Creation | 10 | 3 | 10 | 3 | 100%
Workflow Tracking | 11 | 2 | 10 | 4 | 100%
JDBC Implementation | 11 | 2 | 11 | 4 | 100%
Quality Assurance | 8 | 6 | 8 | 7 | 100%
Test Script Creation | 11 | 2 | 11 | 2 | 100%
Video coordination | 11 | 2 | 11 | 3 | 100%
Github Repo. Creation | 11 | 1 | 11 | 1 | 100%
Gantt Chart Finalization | 11 | 1 | 11 | 2 | 100%
To-Do list Finalization | 11 | 1 | 11 | 2 | 100%
Submission | 13 | 1 | 13 | 1 | 44%